Week 1 — Foundation + Request Module

Goal: Users can submit requests and see them in dashboard.

Day 1

- Create Spring Boot project

- Setup PostgreSQL

- Test DB connection

- Basic folder structure

Day 2

Create base entities:

- User

- Role

- OrganizationDepartment

- ServiceDepartment

Test:

- Save and fetch users

Day 3

Create Request entity:

- Fields from workflow:

  - requester

  - department

  - description

  - required date

  - urgency fields

  - status

MaintenOps Workflow

Day 4

Backend APIs:

- Create request

- Get requests by user

- Duplicate check API

Test with Postman.

Day 5

Frontend setup:

- React + Vite + TypeScript

- Tailwind install

- Basic layout (sidebar + dashboard)

Day 6

Frontend:

- Request form page

- Submit request API integration

Day 7

Frontend:

- Request list page

- Show status

- End-to-end testing

Milestone 1:
User can create and view requests.

Week 2 — Urgency + Quotation System

Goal: Full quotation approval cycle works.

Day 8

Backend:

- Urgency approval APIs

  - Approve

  - Reject

Day 9

Frontend:

- Admin urgency dashboard

- Approve/reject buttons

Day 10

Backend:
Create quotation entities:

- Quotation

- QuotationItem

Day 11

Backend APIs:

- Create quotation

- Submit for SA approval

- Approve quotation (SA)

Day 12

Frontend:

- Admin quotation form

Day 13

Frontend:

- SA approval screen

Day 14

Frontend:

- Requester quotation review

  - Approve

  - Request changes

Milestone 2:
Request → Quotation → Approval flow works.

Week 3 — Lists, Procurement, Production

Goal: System can move from approved quotation to production.

Day 15

Backend:
Entities:

- UserMaterialChecklist

- VendorPurchaseList

- AmountDue

Day 16

Backend:

- Generate lists API

- SA approval for lists

Day 17

Backend:
Procurement:

- Inventory entity

- Mark items purchased API

Day 18

Frontend:

- Vendor purchase list screen

- Mark purchased UI

Day 19

Backend:
Production entities:

- Worker

- ProductionRecord

Day 20

Backend:
APIs:

- Start production

- Approve production start

- Mark production complete

Day 21

Frontend:

- Production dashboard

- Start/complete production

Milestone 3:
System reaches Ready for Collection state.

Week 4 — Payment, Completion, Archival

Goal: Fully working system from start to finish.

Day 22

Backend:
Payment entities:

- PaymentRecord

- CollectionRecord

Day 23

Backend:
APIs:

- Online payment simulation

- Cash payment at collection

- Mark request completed

Day 24

Frontend:

- Payment screen

- Collection screen

Day 25

Backend:

- Completion certificate generation

- Email notifications (basic)

Day 26

Backend:
Archival:

- ArchivedRequest entity

- Archive scheduler

Day 27

Frontend:

- Completed request view

- Download documents

Day 28

Testing:

- End-to-end testing

- Fix bugs

Day 29

UI polish:

- Better layouts

- Status indicators

- Timeline view

Day 30

Final:

- Deployment (local or cloud)

- Demo preparation

Final Milestone:
Full workflow operational from request to archive